## Sheet2
| Call for Proposal | Value of Proposal |  |  | Proposal Due & Approval | Kickoff |  |  |  | IPR1 |  | IPR2 |  | Final PPT | Report/ Video Demo
Week of | 2024-01-11 | 2024-01-18 | 2024-01-25 | 2024-01-01 | 2024-02-08 | 2024-02-15 | 2024-02-22 | 2024-02-29 | 2024-03-07 | 2024-03-14 | 2024-03-21 | 2024-03-28 | 2024-04-04 | 2024-04-11 | 2024-04-18
Task | [5 empty] | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10
3.1 | bar: Week 1
3.2 | bar: Week 1 to Week 3
3.3 | bar: Week 1 to Week 3
3.4 | bar: Week 2 to Week 6
3.5 | bar: Week 3 to Week 7
3.6 | bar: Week 6 to Week 9
3.7 | bar: Week 1; Week 4 to Week 5; Week 7; Week 9 to Week 10
3.1 | Overall planning &Proposal |  |  |  |  | Week 1: Thu 11 Jan ’24 Request for Proposal Sat 10 Feb ’24 Proposal Due Thurs 15 Feb ’24 Project Kickoff Tue 12 Mar ’24 In-Progress Review I – 1st Group Thu 14 Mar ’24 In-Progress Review I – 2nd Group Tue 26 Mar ’24 In-Progress Review II – 1st Group Thu 28 Mar ’24 In-Progress Review II – 2nd Group Tue 9 Apr ’24 Final Project Presentation by 1st Group Thu 11 Apr ’24 Final Project Presentation by 2nd Group Thu 18 Apr ’24 Final Project Report & Video due on Moodle
3.2 | Theoretical Analysis & Design
3.3 | Acquisition & Testing of components
3.4 | Integration & Verification of systems
3.5 | Coding & verification of software
3.6 | Experiments &validation
3.7 | Presentation & demonstration